## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2014-03-05 | 35 | 2014-04-08 | 57 | 68 | Released | 2014-04-09 | Lograr transacciones de datos | 119.3%
2 | 2014-04-09 | 21 | 2014-04-29 | 26 | 42 | Released | 2014-04-30 | Cumplir con reglas de negocio para extraccion de información | 161.5%
3 | 2014-04-30 | 14 | 2014-05-13 | 0 | 0 | Planned | 2014-05-20 | Cumplir con entregables de trabajo de grado
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
1 | 2014-03-05 | 7 | 2014-03-11 | 3 | 4 | Released | 2014-03-12 | Especificación y desarrollo de prototipo | 1 | 33.33%
2 | 2014-03-12 | 14 | 2014-03-25 | 28 | 37 | Released | 2014-03-26 | Especificación y desarrollo de prototipo | 1 | 32.14%
3 | 2014-03-26 | 14 | 2014-04-08 | 26 | 27 | Released | 2014-04-09 | Especificación y desarrollo de prototipo | 1 | 3.846%
4 | 2014-04-09 | 14 | 2014-04-22 | 26 | 26 | Released | 2014-04-23 | Especificación y desarrollo de prototipo | 2 | 0%
5 | 2014-04-23 | 7 | 2014-04-29 | 0 | 16 | Planned | 2014-05-07 | Pruebas de usabilidad, documentación, correcciones | 2 | #DIV/0!
6 | 2014-04-30 | 14 | 2014-05-13 | 0 |  | Planned | 2014-05-14 | Correcciones Memoria TG | 3
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | #VALUE!
|  |  | Total Size | 83 | 110
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog Grupo E-9-56
Story ID | Story name | Planned | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Crear Registros de propietarios | Ongoing | 8 | 1 | 1 | Desarrollo | Se dividieron las tares de la las paginas en el grupo scrum | Se requiere maximo esfuerzo para sacar adelante el proyecto ya que son nuevos conocimeintos
2 | Crear Registro de arrendatarios y/o temporales | Ongoing | 8 | 1 | 1 | Desarrollo | Se dividieron las tares de la las paginas en el grupo scrum | Se requiere maximo esfuerzo para sacar adelante el proyecto ya que son nuevos conocimeintos
3 | Crear Registro y control de visitantes | Ongoing | 9 | 2 | 2 | Desarrollo | Es con estrutura documental | Se requiere maximo esfuerzo para sacar adelante el proyecto ya que son nuevos conocimeintos
4 | Crear Registro de vehículos y mascotas | Ongoing | 8 | 3 | 2 | Desarrollo | Es con estrutura documental | Sin Impacto
5 | Crear Registro de zona comunes e inventario de muebles e inmuebles. | Planned | 8 | 4 | 5 | Desarrollo | Es con estrutura documental | Sin Impacto
6 | Crear Consejo de administracion (cronograma reuniones y actas) | Planned | 8 | 5 | 4 | Desarrollo | Es con estrutura documental | Sin Impacto
|  | Done | 13 | 4 | 4 | Desarrollo | Se realizó según la planeación | Genero Nuevo conocimeinto equipo scrum
|  | Done | 13 | 4 | 4 | Desarrollo | Se realizó según la planeación | Genero Nuevo conocimeinto equipo scrum
1
2
3
4
|  |  | PIBOT | 5
6
7
8
9
10
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.